## Sheet1
# | Trade Package | Indicative Tender Issue Date | Tender Closed | Contract Awarded?
1 | Electrical Services | Completed | Yes | Yes
2 | Security | Completed | Yes | Yes
3 | DAS, ICN, GRN, Ops Radio, Unified Comms, Wifi | Completed | Yes | Yes
4 | AV and PA | Completed | Yes | Yes
5 | Hydraulic Services | Completed | Yes | Yes
6 | Mechanical Services | Completed | Yes | Yes
7 | Fire Services | Completed | Yes | Yes
8 | Vertical Transport and escalators | Completed | Yes | Yes
9A | Sitewide Reticulation - Water, Sanitary, Gas, Stormwater | Completed | Yes | Yes
9A | Sitewide Reticulation - Stormwater | 2021-07-15 | Yes
10 | Concrete | Completed | Yes | Yes
11 | Reinforcement (Supply) | Completed | Yes | Yes
12 | Reinforcement (Fix) | Completed | Yes | Yes
13 | Precast concrete | Completed | Yes | Yes
14 | Formwork | Completed | Yes | Yes
15 | Post Tensioning | Completed | Yes | Yes
16 | Masonry | Completed | Yes | Yes
17 | Structural Steel | Completed | Yes | Yes
18 | Metalwork - Stairs, Ladders, Walkways | 2022-05-15 | Yes
19 | Metalwork - Architectural | 2022-05-15 | Yes
20 | Waterproofing | Completed | Yes | Yes
21 | Thermal insulation | Completed | Yes | Yes
22 | Roofing and siding | Completed | Yes | Yes
23 | Fire and Smoke Protection | Completed | Yes | Yes
24 | Doors, Frames Hardware | Completed | Yes | Yes
25 | Façade - Glazed | Completed | Yes | Yes
26 | Façade - Cladding | Completed | Yes | Yes
27 | Louvers and Vents | Completed | Yes | Yes
28 | Tiling | 2022-05-01 | Yes
29 | Ceilings & Partitions | 2022-05-01 | Yes
30 | Feature Ceiling | Completed | Yes | Yes
31 | Resilient flooring | 2022-05-15 | Yes
32 | Terrazzo flooring | 2022-04-15 | Yes
33 | Epoxy flooring | 2022-02-15 | Yes | Yes
34 | Carpeting | 2022-05-15 | Yes
36 | Stone Cladding | 2022-04-15 | Yes
38 | Painting | 2022-10-15
39 | Signage – static | 2022-05-15 | Yes
40 | Signage – illuminated panel | 2022-05-15 | Yes
41 | Toilet, shower and urinal partitions | 2022-05-01 | Yes
42 | Façade access equipment and fall protection | 2022-05-15 | Yes
43 | Loose Furniture | 2022-07-01 | Yes
44 | Fixed Joinery | 2022-07-01 | Yes
45 | Airside Civil and Earthworks (Apron) | Completed | Yes | Yes
46 | Fuel Pipeline | Completed | Yes | Yes
47 | External area Civil & Earthworks (Carpark, TER & Roads) | 2021-11-10 | Yes
48 | Loading dock equipment | 2022-10-15
49 | Loading Dock Guardhouse | 2022-10-15
50 | Pedestrian control equipment (Signalised) | 2022-10-15
51 | Passenger boarding bridges (Complete) - Aerobridges | Completed | Yes | Yes
52 | Advanced Visual Guidance Docking System | Completed | Yes | Yes
53 | Preconditioned Air Units | Completed | Yes | Yes
54 | Ground Power Units | Completed | Yes | Yes